## Test Cases
Bluechips London — Verotel FlexPay Test Plan
Sandbox test cards: Verotel docs provide test PANs after approval — DO NOT use Stripe test cards (won't work). Verify TEST MODE banner.
ID | Category | Test Name | Pre-conditions | Test Steps | Expected Result | Validation / What to Check | Priority | Status | Notes
PROVIDER WIRING
PR-01 | Provider wiring | Provider config endpoint returns 'verotel' | Backend up. PAYMENT_PROVIDER=verotel in env. | 1. GET /api/payments/config | Returns {provider: 'verotel'}. | Status 200. JSON body matches. Confirms config wiring. | High | Not Run
PR-02 | Provider wiring | Verotel provider fails closed if shop ID missing | VEROTEL_SHOP_ID is blank in .env. | 1. Restart backend. 2. Attempt POST /api/payments/checkout. | Backend returns 503 / clear error. App doesn't expose half-broken checkout. | Logs show ProviderNotConfiguredError. Endpoint responds with provider error. | High | Not Run
PR-03 | Provider wiring | Test mode flag respected | VEROTEL_TEST_MODE=true. | 1. POST /api/payments/checkout. 2. Inspect returned checkout URL. | URL points at Verotel test/sandbox host (or test shopID), not live. | URL contains test shopID or test-mode marker per Verotel docs. No real charge possible. | High | Not Run
CHECKOUT URL
CK-01 | Checkout URL | Essential monthly URL has all required FlexPay params | Email-verified escort, free tier, no pending verification. | 1. POST /api/payments/checkout {tier:'essential', billing:'monthly'}. 2. Parse the returned URL. | URL contains version, type=subscription, shopID, priceAmount, priceCurrency=GBP, period=P1M, email, custom1, signature. | Inspect URL query string — every required param present and correct. | High | Not Run
CK-02 | Checkout URL | Annual billing produces period=P1Y | Free-tier verified escort. | 1. POST checkout with billing='annual'. | URL period param equals P1Y. priceAmount matches platform_config annual amount. | Query string inspection. | High | Not Run
CK-03 | Checkout URL | Signature is valid and matches our local computation | Any valid checkout creation. | 1. Create a checkout session. 2. Extract signature from URL. 3. Recompute locally using VEROTEL_SIGNATURE_KEY and sorted params. | Computed and returned signatures match exactly. | Verify our HMAC-SHA256 implementation matches Verotel's expectation. | High | Not Run
CK-04 | Checkout URL | Discount applies to first charge only, not rebill | FM-xxx code with 50% off active. | 1. POST checkout with discount_code='FM-xxx'. 2. Inspect URL. | priceAmount is ~50% of normal first charge. subscriptionPriceAmount is the full price for rebills. | Reduced priceAmount + nextChargeOn + subscriptionPriceAmount all present. | High | Not Run
CK-05 | Checkout URL | Metadata round-trips via custom1 | Any checkout. | 1. Create checkout. 2. Parse custom1 JSON from URL. | custom1 contains escort_id, tier, billing as a JSON object. | JSON parse of custom1 returns the metadata we passed. | High | Not Run
CK-06 | Checkout URL | Blue Tick combines setup fee + monthly into first charge | Essential-tier escort with no Blue Tick. | 1. POST /api/payments/blue-tick-checkout. | priceAmount = setup_pence + monthly_pence (e.g. £13.99 = £10 + £3.99). subscriptionPriceAmount = monthly only (£3.99). | Inspect URL params. Verify decimal math. | High | Not Run
HOSTED CHECKOUT
HC-01 | Hosted checkout | User redirected from app to Verotel checkout page | Valid checkout URL returned by backend. | 1. Frontend calls createCheckout(). 2. window.location.href = url. | Browser navigates to secure.verotel.com page. Verotel logo + correct product name shown. | Visual check on Verotel hosted page. URL bar shows verotel.com domain. | High | Not Run
HC-02 | Hosted checkout | Test card 4111 1111 1111 1111 (Verotel test mode) succeeds | VEROTEL_TEST_MODE=true. On Verotel test checkout page. | 1. Enter 4111 1111 1111 1111, any future expiry, any CVV. 2. Submit. | Verotel processes test charge. Redirects to our success_url. | URL after redirect matches success_url. Verotel test dashboard shows test sale. | High | Not Run
HC-03 | Hosted checkout | Successful payment redirects to success_url with Verotel-signed params | Just completed test payment. | 1. Land on /dashboard/verify?payment=success&saleID=...&signature=... | URL contains saleID + signature. Our success page handles the redirect. | Browser is on /dashboard/verify page. Frontend doesn't crash. | High | Not Run
HC-04 | Hosted checkout | Declined card returns to cancel_url | On Verotel test checkout. Use a declined test card (per Verotel docs). | 1. Enter declined card. 2. Submit. | Verotel shows decline error. Optional 'try again'. User redirected to cancel_url after giving up. | Land on /dashboard/subscription?payment=cancelled. No DB changes. | High | Not Run
WEBHOOK
WH-01 | Webhook | initial postback creates subscription in DB | User completed a test checkout. | 1. Verotel sends 'initial' postback to /api/webhooks/verotel. 2. Check subscriptions table. | New row created with status='active', tier from metadata, psp_subscription_id = saleID. | DB row exists. escort.subscription_tier updated. escort.psp_subscription_id set. | High | Not Run
WH-02 | Webhook | Invalid signature is rejected with 400 | Webhook secret known. Send a postback with a tampered amount. | 1. POST /api/webhooks/verotel with valid-shape body but signature recomputed from tampered fields. | Endpoint returns 400. No DB mutations. | Webhook events table has NO entry for the bad request. Subscriptions table unchanged. | High | Not Run
WH-03 | Webhook | Missing signature is rejected with 400 | Send postback with `signature` field omitted entirely. | 1. POST /api/webhooks/verotel. | Endpoint returns 400 'Invalid webhook signature'. | InvalidWebhookSignatureError logged. No DB writes. | High | Not Run
WH-04 | Webhook | Duplicate delivery is idempotent | An 'initial' postback has already been processed. | 1. Resend the same postback (same saleID, event, txn). | Second delivery returns {received: true, duplicate: true}. DB unchanged. | webhook_events table has 1 row for the dedup key. No duplicate subscriptions row. | High | Not Run
WH-05 | Webhook | rebill event updates current_period_end | Active subscription. ~30 days after initial. | 1. Verotel sends 'rebill' postback. 2. Check subscriptions row. | current_period_start / current_period_end advance by one month. Status remains 'active'. | DB period fields updated. subscription_expires_at on escort updated. | High | Not Run
WH-06 | Webhook | rebill applies pending downgrade | Active premium sub with pending_tier='essential'. | 1. Wait for / simulate next 'rebill' postback. | tier and escort.subscription_tier flip to 'essential'. pending_tier cleared. | DB updates correctly. Photo-limit check fires (paused if over limit). | High | Not Run
WH-07 | Webhook | cancel event marks status='cancelling' | Active subscription. | 1. User clicks Cancel. 2. Backend calls provider.cancel_subscription. 3. Verotel sends 'cancel' postback. | DB row status='cancelling'. Access continues until period end. | subscriptions.status='cancelling'. escort.subscription_tier still set. | High | Not Run
WH-08 | Webhook | expiry event ends access | Sub in 'cancelling' state. Period has passed. | 1. Verotel sends 'expiry' postback. | status='cancelled'. escort.subscription_tier='free'. psp_subscription_id cleared. | DB. UI shows Free tier on next page load. | High | Not Run
WH-09 | Webhook | uncancel event reactivates | Sub in 'cancelling' state. Admin un-cancelled in Verotel Control Center. | 1. Verotel sends 'uncancel' postback. | status returns to 'active'. | DB row updated. UI shows Active. | Medium | Not Run
WH-10 | Webhook | credit (refund) postback recorded | Refund issued in Verotel Control Center. | 1. Verotel sends 'credit' postback. | subscriptions.cancelled_at set to mark the refund event. Admin should review whether to revoke access. | DB shows refund timestamp. Admin alerted. | Medium | Not Run
WH-11 | Webhook | chargeback instantly revokes access | Customer disputed a charge. | 1. Verotel sends 'chargeback' postback. | subscription cancelled immediately. escort.subscription_tier='free'. escort.is_approved=false. | DB. Escort no longer appears in search. | High | Not Run
WH-12 | Webhook | Unknown event type is logged but returns 200 | Verotel sends an event we don't handle. | 1. POST event with type='something_new'. | Returns 200 (so Verotel doesn't retry forever). Log message captured. | Server logs show '[verotel webhook] Unknown event type'. No DB writes. | Medium | Not Run
WH-13 | Webhook | Webhook handles both POST and GET | Verotel may send GETs in some scenarios. | 1. Test the same postback as both POST body and GET query params. | Both succeed identically. | Same DB outcome from both methods. | Medium | Not Run
SUBSCRIPTION LIFECYCLE
SL-01 | Subscription lifecycle | Cancel via /payments/cancel calls Verotel API | Active subscription. | 1. POST /api/payments/cancel. | Verotel cancel-subscription API hit with correct shopID + saleID + signature. Local sub marked 'cancelling'. | Inspect outgoing request via mock or staging server. DB updated. | High | Not Run
SL-02 | Subscription lifecycle | Cancel of already-cancelled sub is idempotent | Sub already cancelled in Verotel. | 1. Call /payments/cancel again. | Returns success. Verotel 404 treated as success. No errors surfaced to user. | Backend doesn't throw 502 on idempotent cancel. | Medium | Not Run
SL-03 | Subscription lifecycle | Cancel without active sub returns 400 | Free-tier escort. | 1. POST /payments/cancel. | Returns 400 'No active subscription'. | API responds 400. Clear UI message. | Medium | Not Run
SL-04 | Subscription lifecycle | Upgrade triggers cancel + new checkout, NOT in-place modify | Essential subscriber wants Premium. | 1. POST /api/payments/upgrade-tier {tier:'premium'}. | Old sub cancelled. Response returns a NEW checkout URL for premium. Frontend redirects user to it. | Verotel API cancel was called. Response payload contains {url}. User redirected to Verotel page. | High | Not Run
SL-05 | Subscription lifecycle | Reactivation message instructs user to re-subscribe | Cancelling subscription, before period end. | 1. User clicks Reactivate in MySubscriptionsPage. | Toast: 'To reactivate, start a new subscription'. | No backend call (Verotel can't reactivate via API). User pointed to Subscription page. | Medium | Not Run
DISCOUNT CODES
DC-01 | Discount codes | FM- code applies 50% off first charge | Active FM-xxx code with 50%, valid for all tiers. | 1. POST /payments/checkout with discount_code='FM-xxx'. 2. Inspect URL. | First-charge priceAmount = 50% of full price. Subscription rebill price = full. | URL math correct. | High | Not Run
DC-02 | Discount codes | FM- code redemption counter increments | DiscountCode current_redemptions=0. | 1. Complete checkout with the code. | current_redemptions=1 after successful checkout creation. | DB check. | High | Not Run
DC-03 | Discount codes | FM- code grants founding member status | Escort uses FM-xxx code at checkout (not at register). | 1. POST checkout with FM- code. | escort.is_founding_member=true. founding_offer_signups incremented. Prospect linked. | DB: escort + platform_config + outreach_prospects all updated atomically. | High | Not Run
DC-04 | Discount codes | Tier-restricted code rejects wrong tier | Code with applicable_tiers=['premium']. | 1. Try to apply on Essential checkout. | Returns 400 with clear message. | No URL returned. No redemption incremented. | Medium | Not Run
DC-05 | Discount codes | Referral code grants 50% off 3 months | Valid referral_code on another escort. | 1. POST checkout with referral_code. | first-charge discounted 50%. escort.referred_by_code set. | URL math correct. DB updated. | Medium | Not Run
BLUE TICK
BT-01 | Blue Tick | Blue Tick checkout blocked for Premium/Elite | Premium subscriber. | 1. POST /api/payments/blue-tick-checkout. | Returns 400 with helpful message. | No URL. User sees explanatory error. | High | Not Run
BT-02 | Blue Tick | Blue Tick checkout creates pending L3 verification on success | Essential subscriber. Pay Blue Tick via test card. | 1. Complete checkout flow. 2. Verotel sends 'initial' postback. | Verification row created (level=3, status='pending'). Admin email sent. | DB row. Admin email logged in dev logs. | High | Not Run
BT-03 | Blue Tick | Cannot purchase Blue Tick twice | Already has psp_blue_tick_subscription_id. | 1. POST blue-tick-checkout again. | Returns 400 'already have Blue Tick'. | No second checkout URL. | Medium | Not Run
EDGE CASES
EC-01 | Edge cases | Checkout during pending verification returns 409 | Pending L2 verification exists. | 1. POST checkout. | Returns 409 with explanation. | No checkout URL. | High | Not Run
EC-02 | Edge cases | Webhook missing escort_id in metadata falls back to saleID lookup | Postback has empty custom1. | 1. Send postback with custom1=''. | Webhook looks up by psp_subscription_id and finds the escort by that field. | Subscription row updated correctly even without metadata. | Medium | Not Run
EC-03 | Edge cases | Webhook completely orphaned (no escort matches) is silently dropped | Postback references a saleID we never recorded. | 1. Send postback. | Returns 200. Log entry shows could-not-find-escort. | No DB writes. No 500. | Medium | Not Run
EC-04 | Edge cases | Concurrent cancel + rebill race doesn't corrupt state | User cancels at the exact moment a rebill postback arrives. | 1. Send 'rebill' and 'cancel' postbacks within ms of each other. | Final state is consistent — either cancelling+renewed (period extended, will cancel next cycle) or just cancelling. Never both 'active' and 'cancelling' on same row. | DB consistency check. No exceptions raised. | Low | Not Run
PRODUCTION READINESS
PD-01 | Production readiness | VEROTEL_TEST_MODE=false uses live endpoints | Flip env var to false. Restart backend. | 1. Create checkout. | URL points at live Verotel checkout host. WARNING displayed on staging if any real cards used. | URL contains live shopID + live host. | High | Not Run
PD-02 | Production readiness | Webhook URL configured in Verotel Control Center matches our route | Verotel Control Center config check. | 1. Log into Verotel. 2. Check postback URL is https://api.bluechips.live/api/webhooks/verotel. | URL exact match. HTTPS only. | Visual check. | High | Not Run
PD-03 | Production readiness | Signature key + API user/pass match between Verotel and .env | Production .env populated. | 1. Run a test checkout against live Verotel. | Verotel accepts signature. Cancel API call succeeds. | End-to-end live test. | High | Not Run
PD-04 | Production readiness | All FM- codes in prod open to all tiers | Prod DB. | 1. SELECT code, applicable_tiers FROM discount_codes WHERE code LIKE 'FM-%'; | All show applicable_tiers='{}'. | DB query result. | High | Not Run

## Summary
Verotel Test Plan Summary
Category | Total | High | Medium | Low | Notes
Provider wiring | 3 | 3 | 0 | 0
Checkout URL | 6 | 6 | 0 | 0
Hosted checkout | 4 | 4 | 0 | 0
Webhook | 13 | 9 | 4 | 0
Subscription lifecycle | 5 | 2 | 3 | 0
Discount codes | 5 | 3 | 2 | 0
Blue Tick | 3 | 2 | 1 | 0
Edge cases | 4 | 1 | 2 | 1
Production readiness | 4 | 4 | 0 | 0
TOTAL | 47 | 34 | 12 | 1